{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["점검시트"],"not_rendered":{"charts":0,"images":5,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"점검시트","index":0,"n_rows":34,"n_cols":25,"rows_kept":34,"cut":false,"hidden":false,"merged":[[11,15,11,17],[11,2,11,4],[15,2,17,20],[12,2,12,4],[12,9,12,11],[12,12,12,14],[12,18,12,20],[11,9,11,11],[11,12,11,14],[14,2,14,5],[2,1,2,21],[22,2,22,13],[22,14,22,20],[7,2,7,4],[7,5,7,11],[7,12,7,17],[7,18,7,20],[8,2,8,4],[8,5,8,11],[8,12,8,17],[8,18,8,20],[10,2,10,11],[10,12,10,20],[11,5,11,8],[5,2,5,4],[11,18,11,20],[31,2,31,20],[12,15,12,17],[28,4,28,5],[28,6,28,20],[23,2,23,3],[24,5,24,8],[25,9,25,12],[12,5,12,8],[24,2,28,3],[23,15,23,18],[24,15,24,18],[24,19,24,20],[23,19,23,20],[25,15,25,18],[25,19,25,20],[26,9,26,12],[26,15,26,18],[26,19,26,20],[27,4,27,5],[27,6,27,9],[27,10,27,20],[26,5,26,8],[21,1,21,8],[25,5,25,8],[23,5,23,8],[23,9,23,12],[24,9,24,12]]}
[]
[]
[null,"天津法人 2工厂 卷曲/组立 资材 供给用 OHT 稼动前 验收"]
[]
[]
[null,null,"1. 点检概要"]
[]
[null,null,"区分",null,null,"设备名",{"$nulls":6},"制造商",{"$nulls":5},"预计入库日期"]
[null,null,"内容",null,null,"OHT",{"$nulls":6},"GSI"]
[]
[null,null,"验收者",{"$nulls":9},"主要点检内容"]
[null,null,"安全环境",null,null,"小型)组立技术G",null,null,null,"制造商",null,null,"点检日期",null,null,"管理号码",null,null,"检讨结果"]
[null,null,"于林凯",null,null,"金靖",null,null,null,"-",null,null,"2021-08-11",{"$nulls":5},"不允许稼动"]
[]
[null,null,"2. 点检结果概要"]
[null,null,"△ 3方安全认证进行与否\n    →CE认证 进行(SEEM)\n△ 入库前验收结果10件不符合事项确认.(重复件除外)\n△ 向后点检事项\n    → 验收结果整改现况确认\n    → 进行稼动前安全验收.(interlock条件确认)"]
[]
[]
[]
[]
[]
[null,"3. 主要问题点和改善事项"]
[null,null,"改善事项",{"$nulls":11},"计划实施"]
[null,null,"点检对象",null,"일련\n번호","点检结果",null,null,null,"照片",null,null,null,"纳期","完了","措施后照片",null,null,null,"等级"]
[null,null,{"$f":"F9","v":"OHT"},null,1,"脚踏板添加防护角及防滑条\n-水平展开-",{"$nulls":7},"가동전\n稼动前","NG",{"$nulls":4},"C",{"$nulls":4},"样式"]
[{"$nulls":4},2,"安全装置（安全门、光栅、急停按钮）触发后画面变更",{"$nulls":7},"가동전\n稼动前","NG","안전 장치(안전 게이트, 라이트 그리드, 비상 정지 버튼)가 트리거된 후 화면 변경",null,null,null,"C",null,null,"PLC 수정완료"]
[{"$nulls":4},3,"资材托盘投入/排出部为防止托盘重量的夹伤，追加设置圆束安全光栅，未与设备进行联动，测试时触发光栅升降未停止\n-水平展开-",{"$nulls":7},"가동전\n稼动前","NG","팔레트 의 무게의 부상을 방지하기 위해, 팔레트의 입력 / 배출 부, 추가 라운드 빔 안전 격자를 설정, 장치와 연결되지 않은, 테스트 트리거 격자 리프트는 멈추지 않았다\n- 수평 전개 -\"   \n",null,null,null,"A",null,null,"PLC 수정완료"]
[{"$nulls":4},"비 고",null,"수동동작 상태",null,null,null,"1. 도어오픈 후 수동조작 불가로 인한 내부 일부 안전커버 미설치 진행"]
[{"$nulls":4},"验收现况",null,"\n1.安全装置扫描器和保险光栅故障时设备停止条件确认\n  此外升降interlock条件未确认\n2.部分安全装置未确认"]
[]
[]
[null,null,"첨부 1. 설비검수 이력  \n      2. 안전환경 설비인증 입고 검수 SHEET\n     \n   "]
[null,null," ",{"$nulls":17}," 이 상 ."]
[null,null,null,"   ",{"$nulls":9}," "]